## metadata
key | value | description
schema_version | 1.0 | Required. Must remain 1.0 for this template.
project_name | Fictitious Infrastructure Project | Required project or analysis name.
analysis_type | cost | Required: cost or duration.
default_unit | EUR | Required common unit inherited by blank row units.
baseline_estimate | 250000 | Optional finite reference value; not added to simulated totals.
description | Public example containing fictitious values only. | Optional non-confidential context.

## risk_register
name | distribution | minimum | most_likely | maximum | mean | standard_deviation | probability | impact | lambda_shape | category | unit | enabled | notes
Preliminary studies | triangular | 10000 | 15000 | 22000 | [5 empty] | Engineering | EUR | TRUE | Three-point estimate.
Detailed design | pert | 20000 | 30000 | 50000 |  |  |  |  | 4 | Engineering |  | TRUE | Blank unit inherits EUR; lambda defaults to 4 when omitted.
Permitting | uniform | 5000 |  | 12000 | [5 empty] | Regulatory |  | TRUE | All values between minimum and maximum are equally likely.
Site supervision | normal |  |  |  | 18000 | 3000 |  |  |  | Delivery |  | TRUE | Arithmetic mean and standard deviation.
Commodity escalation | lognormal |  |  |  | 25000 | 7500 |  |  |  | Market |  | TRUE | Mean and standard deviation are in arithmetic space.
Regulatory change | event | [5 empty] | 20% | 40000 |  | Regulatory |  | TRUE | Bernoulli occurrence multiplied by a deterministic impact.

## instructions
Risk-register schema 1.0 | How to use this public, non-confidential template.
Workflow | Complete metadata and one active risk per row, save as .xlsx, then run the CLI.
Confidentiality | Never commit real client risk registers. Use anonymized fictitious data only.
Blank cells | Whitespace-only cells and empty cells are treated as blank. Unused parameters stay blank.
enabled | Blank or TRUE means active; FALSE ignores the entire row.
unit | A blank row unit inherits default_unit. Every active item must resolve to the same unit.
baseline_estimate | Optional reference estimate. It is returned as metadata and is never added automatically.
triangular | Required: minimum, most_likely, maximum with minimum <= most_likely <= maximum.
pert | Required: minimum, most_likely, maximum. lambda_shape is optional, defaults to 4 and must be > 0.
uniform | Required: minimum and maximum with minimum <= maximum.
normal | Required: arithmetic mean and standard_deviation >= 0.
lognormal | Required: arithmetic mean > 0 and arithmetic standard_deviation >= 0.
event | Required: probability in [0, 1] and deterministic impact; negative impact can model an opportunity.
Numeric text | Finite numeric strings are accepted; booleans, NaN, infinities and arbitrary text are rejected.
CLI | python -m monte_carlo_simulator.cli --input PATH --simulations 10000 --seed 42 --output-dir data/output